## Tabelle1
Authors: | Das, Hu, Kornberger, Kraker
Phasees and Milestones | Definition | Planning | Hardware development | System Debug | Test Execution | Closure
Date Start | 2024-03-25 | 2024-04-09 | 2024-05-02 | 2024-09-02 | 2024-10-01 | 2024-11-16
Date End | 2024-04-08 | 2024-05-01 | 2024-09-01 | 2024-09-30 | 2024-11-15 | 2024-11-29
Milestone Name | Start | Approval | System Test Start | Start of Test Execution | Release of Test Report | Close
Milestone Date | 2024-04-08 | 2024-05-01 | 2024-09-01 | 2024-09-30 | 2024-11-15 | 2024-11-29
Core Team Member | Project Manager | Project Manager | Validation Engineer | Validation Engineer | Validation Engineer | Project Manager
Activities | Get Chip specification, Plan a Kick Off Meeting, Project one Pager, Define Goals | Timeline plan, cost plan, risk assessment. | Evaluation Board Development, Design Check, Solder Evaluation Board, Testing Evaluation Board, Documentation | System Test of Software and Hardware Validation Framework, Bug fix, | Prepare DUTs for testing, Automated Test Case Implementation, Interpreting Results, Document Results. | Present results, Closure Meeting, Lessons Learned
Effort | Core Team 4 People -> 0.75 Months | Core Team 4 People -> 0.75 Months | 1.5 Validation Eng. 0.5 Chip Architect 2 People -> 4 Months | 1 Validation Eng. 1 Software Eng. 2 People -> 1 Month | 1 Validation Eng. 1 Chip Architect 2 People -> 1.5 Month | Core Team 4 People -> 0.5 Months
Man Months Effort | 3 | 3 | 8 | 2 | 3 | 2
|  | Validation Plan | Software development
Date Start |  | 2024-04-09 | 2024-05-02
Date End |  | 2024-04-25 | 2024-08-15
Milestone Name |  | Validation Plan Release
Milestone Date |  | 2024-04-25
Core Team Member |  | Validation Engineer | Software Engineer
Activities |  | Derive Test Cases | Develope Software Validation Framework, Software Testing, Documentation
Effort |  | 1 Chip Architect 1 Validation Engineer 2 People -> 0.5 Month | 1.5 SW Eng 1 SW Test Eng 2.5 People -> 2.5 Months
Man Months Effort |  | 1 | 6.25
Man Hours Effort Total | 4237.5
Man Effort Cost Total | 423750
Cost Total | 623750